## 工作表1
Story Title | User | user's desire | user's goal (reason for desire) | acceptance criteria | story points | task list | responsible team member | status
server and firewall fixture | for users who want to access our webpage | access to the website | to look for housing options, roomates, or other informations related to housing | The users should still be able to access the web and browse all information on the menu page. | 2 | 1. set up Google server 2. put the desgined index.html into the google server. | Albert, Neveah,David | done
set up an index.html page | for users who want to access our webpage | access to the website | to look for housing options, roomates, or other informations related to housing | The Users can successfully access the page by typing the address in their browser. The users should also be able to browser information and options in the menu page, including login botton,background pictures,feature options. | 2 | 1. Use HTML and CSS to create homepage - react.js? 2. Set links to empty pages 1. information and review link 2. roommate searching link | Bill, Alan,Cynthia | done
Github setup | team members | for team workers to work together and get version control | For the team to better cooperate with others | Github set up | 1 | 1. Create github group and link individual accounts | Albert, Alan | done
Contribute sample housing to database | for users who want to access our webpage | find housing immediately on website launch date | find housing as quickly and easily as possible | user should have a variety to choose from with different price ranges | 8 | 1. Contact different leasing offices around Atlanta Decatur 2. Create spreadsheet with data to be entered into database | Alan, Cynthia | under-way
background image carousel (index.html) | for users who want an aesthetic front page to our website | view sample pictures of flagship housing locations | get a representative idea of the sort of housing that you will find on the website | randomized image for different locations | 2 | 1. search for relevant images 2. Use HTML and CSS to display images on our homepage | Cythia, Bill | done