## Sheet1
Story Title | User | user's desire | user's goal (reason for desire) | acceptance criteria | story points | task list | responsible team member | status
login and registration form design | for users who want to post reviews and find roommates. | Find roommates and write reviews for housing. | Ultimately to find suitable housing. | users can log in, update their profile and perference post reviews and interact with other users using their emory email | 5 | 1. design basic login form (including enter username, password, forgot password, link to sign up page) 2.design sign up form (including enter email, type in password, retype in password) | Bill, Cynthia | done
make login and sign up form visible onclick login/sign up button | for users who want to post reviews and find roommates. | Find roommates and write reviews for housing. | Ultimately to find suitable housing. | users can log in, update their profile and perference post reviews and interact with other users using their emory email | 3 | 1.use AngularJS library to write funtion that can hide and show divisions in html | Bill, Cynthia | done
create user table (database) | for users who want to log in, post information and look for roommates | access to the website, log in, post information | to find matched roommates, post reviews, etc. | The database should store user's emory email (as user name), password, profile(name, contact, housing preference, rommate prefence) | 5 | 1.use mysql on virtual machine to create new database for GoHousin project 2.design and create tables for user login and profile. | Albert Li | done
user table relational schema | for team members to manage database | manage database | build the sql table according to relational schema | relational schema is easy to read, clearly indicate the relations between each table | 3 | 1. create relational schema using ERDPlus 2. upload the relational schema to team folder | Nevaeh | done
16