## Sheet1
Story Title | User | user's desire | user's goal (reason for desire) | acceptance criteria | story points | task list | responsible team member | status
housing information navigation page | for users that want to view an aesthetic housing information listing | read housing information in a systematic order | ultimately to find suitable housing. | user can read the housing information and the frontend page can be linked to the backend database | 3 | 1. design a navigation bar that allows users go to other pages of our website and we will use this navigation bar for all other pages 2. design the body of the housing information navigation page | Cynthia | done
about us page | for users that want to see the company mission | find out more information about the company | users can understand our motivaton and our idea | user can see developer contact information and company mission | 2 | 1. write company mission 2. display developer profile images and names | Alan | done
contact us page | for users who want to contact us | get our contact information | find a way to talk to us | users can find out a way to contact us and get timely repsonse | 2 |  | Nevaeh | under-way
Back-end to signup | Users trying to signup | get an gohousing account | to enjoy more functions and features of the website | users can sign up an account and profile will be added to database | 3 | 1.using php to implement signup-function 2.implementing a new html(primitive ) profile page. | Albert | done