## Sheet1
Story Title | User | user's desire | user's goal (reason for desire) | acceptance criteria | story points | task list | responsible team member | status
redesign housing information navigation page | for users that want to view an aesthetic housing information listing | read housing information in a systematic order | ultimately to find suitable housing. | user can read the housing information and the frontend page can be linked to the backend database | 3 | 1. redesign the structure of the navigation page and make it looks more professional 2. Add basic information of different housing options | Cynthia | done
design and implement gables montclair housing information review page | for users that want to view an aesthetic housing information of Gables Montclair | read housing information of Gables Montclair in a systematic way | ultimately to find suitable housing | user can read Gables Montclair housing information and other housing information page can follow the same structure | 5 | 1.design the structure of the housing information review page 2. Add the basic information of Gables Montclair | Cynthia | done
implement other housing information pages follow the gables example | for users that want to view an aesthetic housing information of communities around Emory | read housing information of communities around Emory in a systematic way | ultimately to find suitable housing | user can read housing information of communities around Emory | 8 | 1.follow the same structure that has been designed in previous step and add basic information into it. | Cynthia | underway
make website be responsive to small size screen | for user who use mobile terminals to view our website | want to get access to our website using portable devices | ultimately to find suitable housing | user can have a clear view of our website on small-sized screens | 3 | use @media function of CSS to redesign index page | Bill | done
Back-end sign in function | for account holders | to log into our website | to use all our features | users can log in their accounts and their personal page | 3 | set up a new php for personal homepage. | Albert | done
contact us page | for users who want to contact us | get our contact information | find a way to talk to us | users can find out a way to contact us and get timely repsonse | 5 | 1. contact us page design 2. put the user input messages to database | Nevaeh | underway