## Sheet1
Story Title | User | user's desire | user's goal (reason for desire) | acceptance criteria | story points | task list | responsible team member | status
implement other housing information pages follow the gables example | for users that want to view an aesthetic housing information of communities around Emory | read housing information of communities around Emory in a systematic way | ultimately to find suitable housing | user can read housing information of communities around Emory | 8 | 1. implement Emory Point page 2.implement Highland Lake page 3.implement Highland Square page | Nevaeh | done
profile page frontend + backend | for every user who has registered in gohousin platform | read basic information that has been entered into profile | know they have been registered and signed in successfully | user can read their basic information | 5 | 1.design and implement profile front end 2. link to the backend database to retrieve user basic information | Albert, Cynthia | underway
contact us page | for users who want to contact us | get our contact information | find a way to talk to us | users can find out a way to contact us and get timely repsonse | 5 | 1. contact us page design 2. put the user input messages to database | Albert, Nevaeh | done
Set up Email System | for our account holders | to receive email from our website | contact/forgot password/roomate search | can reveive email from website | 8 | 1.download mail system ssmtp system 2.configure emial system to access email sending account 3.using php to implement auto-email function | Albert | done
information sharing frontend (blog) | for user who wants to share their own information or send inquries | find possible roommate/ share their personal experience with housing / share any other information | sharing personal information | user can add/delete/edit posts amd make those posts available to other users | 8 | 1. install wordpress 2. install blog component 3. connect to backend | Bill | underway