## Sheet1
story titles | User | user's desire | user's goal (reason for desire) | acceptance criteria | story points | task list | responsible team member | status
review frontend | for users that want to view an aesthetic housing review listing | read housing reviews of communities around Emory | ultimately to find suitable housing | user can read housing review of communities around Emory | 5 | 1. use gables montclair as an example to create a space for user to input review 2. list historical user reviews | Cynthia, Alan | done
roommate search form | for users who want to search for roommate | find roommates who have similar habits | to find a roommate that the can live comfortably together | design a form where users fill in their preferences, and we match them with people with similar habits | 5 | 1. A form where users enter their preference using checkbox 2. connect the data with backend database | Nevaeh | done
information sharing frontend (blog) | for user who wants to share their own information or send inquries | find possible roommate/ share their personal experience with housing / share any other information | sharing personal information | user can add/delete/edit posts amd make those posts available to other users | 8 | 1. create a homepage for information sharing blog(similiar to homepage of the website) 2. create a forum based on wordpress (create backend using wordpress) 3. add three basic topics to the forum | Bill | done
information review backend(database + php) | for users who want to store and retrieve reviews in our database | write/retrieve reviews of different housing options around emory | know more information that won't be provided by leasing office | user can write and retrieve the reviews of housing options around emory | 8 | 1.load previous review from databases and format them on page 2.use session variebles and post method to insert the review into database if user want to add review | Albert | done
roommate searching frontend | for users who want an aesthetic roommate searching design | find roommates who have similar habits | to find a roommate that the can live comfortably together | Aesthetic and secure messenger that allows Emory users in the user table to contact each other | 5 | 1.follow the style of gables montclair page to implement all the other housing review pages | Bill, Nevaeh | underway
implement all review frontend | for users that want to view an aesthetic housing review listing | read housing reviews of communities around Emory | ultimately to find suitable housing | user can read housing review of communities around Emory | 5 | 1. A platform that can either direct users to fill in roommate searching form or to review the matching roommates | Cynthia | underway