## Sheet1
story titles | User | user's desire | user's goal (reason for desire) | acceptance criteria | story points | task list | responsible team member | status
profile page frontend + backend | for every user who has registered in gohousin platform | read basic information that has been entered into profile | know they have been registered and signed in successfully | user can read their basic information | 5 | 1. make a profile page that can retrieve basic information about user from database 2. link it with review/roommate searching page if user hasn't logged in yet | Cynthia, Albert | done
implement all review frontend | for users that want to view an aesthetic housing review listing | read housing reviews of communities around Emory | ultimately to find suitable housing | user can read housing review of communities around Emory | 5 | 1. follow the styles of gables montclair page and implement all the other housing pages | Alan | done
Information sharing backend | for user who wants to share their own information or send inquries | find possible roommate/ share their personal experience with housing / share any other information | sharing personal information | user can add/delete/edit posts amd make those posts available to other users | 8 | 1. create a homepage for information sharing blog(similiar to homepage of the website) 2. create a forum based on wordpress (create backend using wordpress) 3. add three basic topics to the forum | Bill | done
roommate searching frontend | for users who want an aesthetic roommate searching design | find roommates who have similar habits | to find a roommate that the can live comfortably together | Aesthetic and secure messenger that allows Emory users in the user table to contact each other | 8 | 1. survey design 2. upon finishing survey, we will show the profiles of those who match with the user | Nevaeh | done
roommate searching backend | for us to retrieve survey result and compare them with other users | for us to store survey result into database | manage user's habit | survey result can be stored in and retrieved from database | 8 | 1. store json file into database 2. retrieve from database as json file | Nevaeh, Albert | underway