## Sheet1
story titles | User | user's desire | user's goal (reason for desire) | acceptance criteria | story points | task list | responsible team member | status
roommate searching backend | for us to retrieve survey result and compare them with other users | for us to store survey result into database | manage user's habit | survey result can be stored in and retrieved from database | 8 | 1. store json file into database 2. retrieve from database as json file | Nevaeh, Albert | done
rewrite survey page | developer | for us to better integrate the survey result into our databse | store survey result into our databse | A form which users fill in their preferences, and we match them with people with similar habits | 5 | 1. design and implement the survey using php and html | Cynthia | done
Debug and wrap up | developer | test and debug the website to wrap up the project | wrap up the project | The user can use the website as they want. | 13 | 1. run through the website and detect possible bugs 2. fix the bugs | All members | done